# Vora Mechanical Intern Tasks

GOAL: Build a fully functional MATLAB simulation, validated against an EnergyPlus co-simulation, that demonstrates at least 25 percent AC energy savings while holding indoor comfort within range of +-0.5 of ASHRAE 7-points thermal satisfaction scale .

Primary focus: MATLAB simulation and MATLAB and EnergyPlus co-simulation, alongside the continuous controls research

| # | Task | Owner | Start | Deadline | Depends On |
| --- | --- | --- | --- | --- | --- |
| S1 | Onboard. Study the problem Vora is solving, the AI Climate Engine product, the value proposition, and the target personas (bill pressured apartment residents, multi room villa families, B2B clinic). Review the existing MATLAB simulation from S1. | Intern + Huzayfa | Jun 9 | Jun 9 |  |
| S2 | Literature and method review. Survey AC and HVAC energy optimization and control strategies (thermostat, scheduling, pre cooling, MPC, reinforcement learning). Note reported savings ranges and key references. Deliver a detailed report. | Intern | Jun 9 | Jun 11 | S1 |
| S3 | Tooling setup. MATLAB and Simulink, EnergyPlus, a shared Git repository, and Doha weather files (EPW or TMY). Confirm a baseline EnergyPlus run completes end to end. | Intern | Jun 14 | Jun 14 | S2 |
| S4 | Define scope and the success metric. Fix the building archetypes, the comfort band (ASHRAE 55), the energy metric (kWh and percent savings), and the exact baseline that the 30 to 50 percent target is measured against. | Intern + Huzayfa | Jun 15 | Jun 15 | S3 |

| # | Task | Owner | Start | Deadline | Depends On |
| --- | --- | --- | --- | --- | --- |
| S5 | Build a lumped RC thermal model of a representative Doha apartment in MATLAB and Simulink. Start at 1R1C, then extend to 2R2C or 3R3C for better accuracy. | Intern | Jun 16 | Jun 21 | S4 |
| S6 | Model the AC vapor compression system. Cooling capacity and COP or EER as functions of outdoor temperature and part load. Include both sensible and latent (humidity) load, which is critical in the Gulf climate. Reuses the EES cycle simulation experience. | Intern | Jun 22 | Jun 24 | S5 |
| S7 | Integrate weather, occupancy, and solar and internal gains. Drive the combined model with Doha summer TMY data. | Intern | Jun 25 | Jun 25 | S6 |
| S8 | Implement the baseline thermostat control (on or off hysteresis with a fixed setpoint schedule). Produce the baseline energy profile that everything else is compared against. | Intern | Jun 28 | Jun 29 | S7 |
| S9 | Calibrate and sanity check the model against literature and any available real bills or Kahramaa data. Document all assumptions and limits. | Intern + Huzayfa | Jun 30 | Jun 30 | S8 |

| # | Task | Owner | Start | Deadline | Depends On |
| --- | --- | --- | --- | --- | --- |
| S10 | Build an EnergyPlus model of the same apartment. Geometry, envelope for typical Qatar construction, schedules, an HVAC template, and the Doha EPW file. New tool for Intern, high value for credibility. | Intern | Jul 1 | Jul 5 | S9 |
| S11 | Validate the EnergyPlus baseline against the MATLAB RC baseline. Reconcile and document the differences between the two models. | Intern | Jul 6 | Jul 7 | S10 |
| S12 | Stand up the MATLAB to EnergyPlus co simulation. Exchange setpoint and state each timestep using the EnergyPlus Python API and EMS, or BCVTB or MLE+. | Intern | Jul 8 | Jul 13 | S11 |
| S13 | Validate the co simulation loop with the baseline controller. Confirm timing, numerical stability, and that results match the standalone runs. | Intern | Jul 14 | Jul 16 | S12 |

| # | Task | Owner | Start | Deadline | Depends On |
| --- | --- | --- | --- | --- | --- |
| S14 | Implement rule based optimizations. Setback when unoccupied, pre-cooling that exploits building thermal mass, and peak shifting. Quantify savings versus the baseline. This is the must have layer. -not confirmed task, mostly We will use already done rule-based that | Intern + Huzayfa | Jul 19 | Jul 21 | S13 |
| S15 | Implement Model Predictive Control using weather and occupancy forecasts, a comfort constraint, and an energy objective. This is the shared controls research track. Reach target rather than must have. | Intern + Huzayfa | Jul 22 | Jul 27 | S14 |
| S16 | Tune and iterate to reach 30 to 50 percent savings while holding the comfort band. Produce a clear comparison of baseline versus each strategy on both the MATLAB and the EnergyPlus models. | Intern | Jul 28 | Jul 29 | S15 |

| # | Task | Owner | Start | Deadline | Depends On |
| --- | --- | --- | --- | --- | --- |
| S17 | Define the faults worth detecting (coil fouling, low refrigerant charge, clogged filter, sensor drift) and their signatures in energy, temperature, and efficiency. Directly leverages the condition monitoring background. | Intern | Jul 30 | Jul 30 | S16 |
| S18 | Build a fault detection module. Inject simulated faults and detect them through COP and efficiency degradation and data signatures. Reuse FFT and condition monitoring methods where they help. Maps directly to Vora maintenance detection. | Intern | Aug 2 | Aug 2 | S17 |

| # | Task | Owner | Start | Deadline | Depends On |
| --- | --- | --- | --- | --- | --- |
| S19 | Extend the simulation to the villa and clinic archetypes. Run savings and comfort across all three Vora personas, not just the apartment. | Intern | Aug 5 | Aug 6 | S18 |
| S20 | Translate kWh savings into QAR bill savings using the Kahramaa tariff structure, and connect this to the Vora bill sharing revenue model. Leans on the KAHRAMAA experience. | Intern + Huzayfa | Aug 7 | Aug 7 | S19 |
| S21 | Run a sensitivity and robustness analysis across weather variation, occupancy patterns, and model mismatch, so the savings claim holds up under scrutiny. | Intern | Aug 8 | Aug 8 | S20 |

| S23 | Consolidate into a clean, documented, parametrized MATLAB simulation with the EnergyPlus co simulation. Add a README and make every run reproducible. | Intern | Aug 9 | Aug 9 | S22 |
| --- | --- | --- | --- | --- | --- |